## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35 | ** Need to redo these
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8
As a customer I want to have member booking so that I do not have to remember my contact info
As a customer I want to have member booking so that I can get special discounts off my booking
As a owner I want to support loyality points to that customers can redeem for a deal
As an owner I want to see what my customers are looking at so that I can provide customer specific offers
As a payment provideer I want a payment API that can hamdle different tax rates
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction
As a customer I want to get alerts on bookings and new deals so that I can know about deals
As an owner I want to support A/B testing so that I can optimize ad placement for revenue
Note on D18: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
Note on B7: Dan Penny: Create taskss breakdown for 4 stories with top ROI

## Product Backlog - Meeting 3
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores
As a payment provider I want an Payment API available so that I can troubleshoot payment issues
As a payment provider I want an Payment API available so that I can see all payments on a date
As a payment provider I want Payment info in a database so that I can see all my data for reports
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly
As a hotel customer I want a webpage details page so that I can view my payment status
As a hotel owner I want a payment details portal so that I can assist my customers
As a hotel customer I want a user portal so that I can cancel my booking
As a hotel customer I want a user portal so that I can edit my booking
As a customer I want to have member booking so that I do not have to remember my contact info
As a customer I want to have member booking so that I can get special discounts off my booking
As a owner I want to support loyality points to that customers can redeem for a deal
As an owner I want to see what my customers are looking at so that I can provide customer specific offers
As a payment provideer I want a payment API that can hamdle different tax rates
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction
As a customer I want to get alerts on bookings and new deals so that I can know about deals
As an owner I want to support A/B testing so that I can optimize ad placement for revenue
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices)
As a customer I want to get an email notification of payment so that I can have proof of payment
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
As a customer I want to have an option to book a meeting hall so that I can online book an event
As a hotel owner I want a special role so that I can have different access for different users ( admin/users)
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle

## Product Backlog - Meeting 4
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores
As a payment provider I want an Payment API available so that I can troubleshoot payment issues
As a payment provider I want an Payment API available so that I can see all payments on a date
As a payment provider I want Payment info in a database so that I can see all my data for reports
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly
As a hotel customer I want a webpage details page so that I can view my payment status
As a hotel owner I want a payment details portal so that I can assist my customers
As a hotel customer I want a user portal so that I can cancel my booking
As a hotel customer I want a user portal so that I can edit my booking
As a customer I want to have member booking so that I do not have to remember my contact info
As a customer I want to have member booking so that I can get special discounts off my booking
As a owner I want to support loyality points to that customers can redeem for a deal
As an owner I want to see what my customers are looking at so that I can provide customer specific offers
As a payment provideer I want a payment API that can hamdle different tax rates
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction
As a customer I want to get alerts on bookings and new deals so that I can know about deals
As an owner I want to support A/B testing so that I can optimize ad placement for revenue
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices)
As a customer I want to get an email notification of payment so that I can have proof of payment
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
As a customer I want to have an option to book a meeting hall so that I can online book an event
As a hotel owner I want a special role so that I can have different access for different users ( admin/users)
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle
As a hotel owner I want a search option based on dates so that customer can see room availibility
As a hotel owner I want a to provide the customer with a flexible refund process so that they can get instant refund in terms of points
As a hotel owner I want my website to have B2B so that I connect to travel agents to offer them discouted rates
As a customer I want events tab on the website so that I can get information on ongoing and scheduled evernts
As a hotel owner I want to provide a complementary option for the first 5% of customers(per day) so that I can attract more customers
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa
As a customer I want to be able to login using social media so that they have easy access

## Retro
Team Member | Worked | Did not work
<Member1>

## Team Members
Name | A# | Role
Person 1 |  | Product Owner
Person 2 |  | ScrumMaster
Person 3 |  | Team Member
Person 4 |  | Team Member
Person 5 |  | Team Member
Person 6 |  | Team Member